## Introduction
| Tejidos Especiales e-Dentel. Planner | [6 empty] | Introduction
Aggregate planning
Tejidos Especiales e-Dentel (B) provides a reasonable size exercise on which to test some of the ideas
you may have come up with to resolve the A case. Working with a small exercise has one
advantage: if your proposed approach does not work, you find it quicker, but it also has a disadvantage:
an approach which works on a small problem does not provide any guarantee that it will work on a
real life size problem. The time required to find a solution can make it unfeasible.
This exercise concentrates on the Planning-Sales interface. Note that the information that Sales needs
to obtain from Planning is not a very detailed one (e. g., in terms of which machines will be assigned
to this job) but it needs to cover a rather long horizon. Therefore, we can use the aggregate planning
ideas, by drawing a cumulative chart of promised delivery loads and compare it with the cumulative
available capacity.
Even though at first sight it appears that it is possible to deliver the jobs as promised, because there
is enough capacity ( 20 machines for 15 days to manufacture a load of 252 machine-days), a closer look
reveals that the last job must be delivered by day 12. Therefore we only have 20*12 = 240 machine-days
of available capacity to satisfy a demand of 252.
Even if we delay the low priority jobs (a total of 13 machine-days of load) to day 15, it is not sufficient
to make it feasible. The check we just made to see if the available capacity in 12 days is enough to make
everything that needs to be deliver in the first 12 days, must be repeated for every day. The following
pivot table shows the capacity and promised deliveries according to the original dates, assuming that
capacity is limited to 20 machine-days/day.
| Prior. |  |  | Cum. | Cum | Cum.
Delivery | N | H | L | H + N | H+N+L | Capac.
3 | 2 | 6 |  | 8 | 8 | 60
4 | 8 | 4 |  | 20 | 20 | 80
5 | 16 |  | 8 | 36 | 44 | 100
6 | 22 | 22 |  | 80 | 88 | 120
7 | 29 | 14 | 5 | 123 | 136 | 140
8 | 18 | 18 |  | 159 | 172 | 160
9 | 44 |  |  | 203 | 216 | 180
10 | 20 |  |  | 223 | 236 | 200
11 | 12 |  |  | 235 | 248 | 220
12 | 4 |  |  | 239 | 252 | 240
Total | 175 | 64 | 13
Prof. Jaume Ribera
IESE 2001

## Intro2
| Tejidos Especiales e-Dentel. Planner | Introduction
The following chart presents the cumulative demand and production capacity when all jobs are
scheduled to be delivered at their promised date. We can see that the demand curve exceeds the
available supply already in day 8.
We are offered the possibility of delaying normal jobs by up to 2 days and low priority jobs as much
as needed. If we plan for a crash approach (delaying each job as much as possible within these
constraints), we obtain a feasible solution
|  |  | 1 | -100 | -87 | 87
|  |  | 2 | -200 | -192 | 105
|  |  | 3 | -300 | -302 | 110
|  |  | 4 | -400 | -406 | 104
|  |  | 5 | -500 | -534 | 128
|  |  | 6 | -600 | -642 | 108
|  |  | 7 | -700 | -787 | 145
|  |  | 7 | 300 | 213 | 73
|  |  | 8 | 200 | 160 | 53
Question: If a salesman approaches you asking whether a new order for 50 machine-days to be delivered |  |  | 9 | 100 | 56 | 104
on day 5 can be accepted, what would you reply? |  |  | 10 | 0 | -32 | 88
|  |  | 11 | -100 | -97 | 65
|  |  | 12 | -200 | -205 | 108
|  |  | 13 | -300 | -304 | 99
|  |  | 14 | -400 | -394 | 90
|  |  | 15 | -500 | -519 | 125
|  |  | 16 | -600 | -629 | 110
|  |  | 17 | -700 | -713 | 84
88

## Intro2Yes
| Tejidos Especiales e-Dentel. Planner | Introduction
Note that by accepting a new order to be delivered on day 5, not only the curve value for day 5 changes,
but also those points after day 5. Remember the curve is the cumulative demand up to a given day?
So, if the new order is accepted, it can be delivered on time, but this will create conflicts to deliver
other orders on time, so they will have to be delayed.

## Intro2No
| Tejidos Especiales e-Dentel. Planner | Introduction
Right !!. Accepting this order would move not only the point for day 5, but all the points after day 5,
making other orders to become delayed.
So, if the new order is to be accepted, other orders will have to be delayed,
to satisfy the capacity constraints of the plant.

## Intro3
| Tejidos Especiales e-Dentel. Planner | Introduction
In fact, the amount available to promise at any time is part of the information required by the Sales
department. This information can be presented as a chart, computing the minimum slack available
from each date onwards. For the same example, this is the corresponding chart:
As can be seen from the chart above, the maximum capacity available to promise in days 1 to 12 is
17 machine-days.

## Intro4
| Tejidos Especiales e-Dentel. Planner | [5 empty] | How to use
In the following chart you will have the opportunity to adjust the original plan to make it feasible.
You can change the promised delivery date of any order, sort the table and check the effects of your
changes, both in the cumulative curves (to check feasibility) and in the scatter chart which compare
the promised delivery date with the currently planned date.
You can work on the worksheet either making changes manually or by applying some predefined
algorithms to find a feasible solution.
Manually
Reset | Resets the table to the original situation
Sort | After making changes in the Pr. Del. (Promised Delivery) column, press this button to
sort the table according to the sequence of delivery dates promised. You can then
check the possible delays.
Cum | Shows the cumulative charts for capacity and promised deliveries
Check | Shows the scatter diagram comparing promised date with the earliest possible delivery
Optimize | Offers several pre-programmed solutions. Check the button below to obtain an explanation
of the details behind the computations
| Shortest time first |  | It sorts jobs according to its process time.
| Min Max Delay |  | Sequences the jobs so as to minimize the maximum delay.
| Min Numb. Del. |  | Sequences the jobs to minimize the number of jobs delayed.
| Critical ratio |  | Schedules jobs according to the Order/Delivery ratio
| Slack |  | Schedules jobs according to the difference Delivery-Order
Cum | Shows the cumulative charts for capacity and promised deliveries
Check | Shows the scatter diagram comparing promised date with the earliest possible delivery
Combine | You can start with one of the optimized solutions and modify it manually to obtain a
"better" solution, e.g., one that takes priorities into account.
In addtion to the charts, the worksheet displays several statistics realted to the proposed schedule:
No. Jobs late: | Perc. Jobs late | Avg. delay | Max. Delay | Weight. delay | Cum. Invent. | Note: Statistics are only available for feasible plans. If your current plant is not feasible (we cannot deliver as promised) no statistics are computed.
5 | 15.62% | 4.2 | 5 | 69 | 1395
Most of the statistics are self-explanatory. These are not so obvious:
Weighted delay |  | For each delayed job it computes the sum of its delay by the order size and it
weigths according to priority: Low - 1, Normal - 5, High - 10. The statistic is the
sum of all these values.
Cumul. inventory |  | Number of machine-days of advanced production, computed if the job is completed
before its delivery date. It does not consider WIP inventory.

## Work
[9 empty] | No. Jobs late: | Perc. Jobs late | Avg. delay | Max. Delay | Weight. delay | Cum. Invent.
NOT FEASIBLE | [8 empty] | 0 | 0% | #DIV/0! | 0 | 0 | 834
Cust. | Order | Pr. Del. | Seq. | Prior. | Comments | Plan Av. | Calcul1 | Calcul2 | Cum. Ord | Cum Cap. | Dif. | Orig. | Late | Delay |  |  |  |  | Calcul1 | Order | Cum. Ord | Available
|  | 0 | [6 empty] | 0 | 0 | [8 empty] | 0 | 0 | 0
A137 | 2 | 3 | 1 | N |  | 1 | 3 | 0.2 | 2 | 60 | 58 | 3 | 0 |  | 5 | 0 | 0 | 0 | 3 | 2 | 2 | 1
A100 | 6 | 3 | 2 | H | Risk of cancellation | 1 | 3 | -0.3 | 8 | 60 | 52 | 3 | 0 |  | 10 | 0 | 15 | 15 | 3 | 6 | 8 | 1
A400 | 4 | 4 | 3 | H |  | 1 | 4 | 0 | 12 | 80 | 68 | 4 | 0 |  | 10 | 0 |  |  | 4 | 4 | 12 | 1
B108 | 8 | 4 | 4 | N |  | 1 | 4 | -0.8 | 20 | 80 | 60 | 4 | 0 |  | 5 | 0 | 0 | 0 | 4 | 8 | 20 | 1
A238 | 6 | 5 | 5 | N |  | 2 | 5 | -0.2 | 26 | 100 | 74 | 5 | 0 |  | 5 | 0 | 15 | 300 | 5 | 6 | 26 | 2
A401 | 8 | 5 | 6 | L |  | 2 | 5 | -3 | 34 | 100 | 66 | 5 | 0 |  | 1 | 0 |  |  | 5 | 8 | 34 | 2
B400 | 10 | 5 | 7 | N | Admits partial deliveries | 3 | 5 | -1 | 44 | 100 | 56 | 5 | 0 |  | 5 | 0 |  |  | 5 | 10 | 44 | 3
B007 | 10 | 6 | 8 | H | Should at least deliver half of it on time | 3 | 6 | -0.4 | 54 | 120 | 66 | 6 | 0 |  | 10 | 0 |  |  | 6 | 10 | 54 | 3
C018 | 10 | 6 | 9 | N | Admits deliveries ahead of time | 4 | 6 | -0.8 | 64 | 120 | 56 | 6 | 0 |  | 5 | 0 |  |  | 6 | 10 | 64 | 4
B009 | 12 | 6 | 10 | H |  | 4 | 6 | -0.6 | 76 | 120 | 44 | 6 | 0 |  | 10 | 0 |  |  | 6 | 12 | 76 | 4
C017 | 12 | 6 | 11 | N | Admits deliveries ahead of time | 5 | 6 | -1.2 | 88 | 120 | 32 | 6 | 0 |  | 5 | 0 |  |  | 6 | 12 | 88 | 5
B105 | 4 | 7 | 12 | N |  | 5 | 7 | 0.6 | 92 | 140 | 48 | 7 | 0 |  | 5 | 0 |  |  | 7 | 4 | 92 | 5
A200 | 5 | 7 | 13 | L | Admits deliveries ahead of time | 5 | 7 | 2 | 97 | 140 | 43 | 7 | 0 |  | 1 | 0 |  |  | 7 | 5 | 97 | 5
A203 | 5 | 7 | 14 | N | Admits deliveries ahead of time | 6 | 7 | 0.4 | 102 | 140 | 38 | 7 | 0 |  | 5 | 0 |  |  | 7 | 5 | 102 | 6
A219 | 10 | 7 | 15 | N |  | 6 | 7 | -0.6 | 112 | 140 | 28 | 7 | 0 |  | 5 | 0 |  |  | 7 | 10 | 112 | 6
A537 | 10 | 7 | 16 | N |  | 7 | 7 | -0.6 | 122 | 140 | 18 | 7 | 0 |  | 5 | 0 |  |  | 7 | 10 | 122 | 7
A211 | 14 | 7 | 100 | H | Risk of cancellation | 7 | 7 | -0.7 | 136 | 140 | 4 | 7 | 0 |  | 10 | 0 |  |  | 7 | 14 | 136 | 7
B455 | 3 | 8 | 17 | N |  | 7 | 8 | 1 | 139 | 160 | 21 | 8 | 0 |  | 5 | 0 |  |  | 8 | 3 | 139 | 7
A101 | 3 | 8 | 18 | H |  | 8 | 8 | 0.5 | 142 | 160 | 18 | 8 | 0 |  | 10 | 0 |  |  | 8 | 3 | 142 | 8
B217 | 5 | 8 | 19 | N |  | 8 | 8 | 0.6 | 147 | 160 | 13 | 8 | 0 |  | 5 | 0 |  |  | 8 | 5 | 147 | 8
B107 | 10 | 8 | 20 | N |  | 8 | 8 | -0.4 | 157 | 160 | 3 | 8 | 0 |  | 5 | 0 |  |  | 8 | 10 | 157 | 8
B128 | 15 | 8 | 100 | H | Risk of cancellation, Good customer! | 9 | 9 | -0.7 | 172 | 160 | -12 | 8 | 0 |  | 10 | 0 |  |  | 8 | 15 | 172 | 9
A470 | 4 | 9 | 21 | N |  | 9 | 9 | 1 | 176 | 180 | 4 | 9 | 0 |  | 5 | 0 |  |  | 9 | 4 | 176 | 9
A431 | 10 | 9 | 22 | N |  | 10 | 10 | -0.2 | 186 | 180 | -6 | 9 | 0 |  | 5 | 0 |  |  | 9 | 10 | 186 | 10
B213 | 10 | 9 | 23 | N |  | 10 | 10 | -0.2 | 196 | 180 | -16 | 9 | 0 |  | 5 | 0 |  |  | 9 | 10 | 196 | 10
B800 | 20 | 9 | 100 | N | Admits partial deliveries | 11 | 11 | -2.2 | 216 | 180 | -36 | 9 | 0 |  | 5 | 0 |  |  | 9 | 20 | 216 | 11
A503 | 10 | 10 | 24 | N |  | 12 | 12 | 0 | 226 | 200 | -26 | 10 | 0 |  | 5 | 0 |  |  | 10 | 10 | 226 | 12
A138 | 10 | 10 | 25 | N |  | 12 | 12 | 0 | 236 | 200 | -36 | 10 | 0 |  | 5 | 0 |  |  | 10 | 10 | 236 | 12
B813 | 4 | 11 | 26 | N |  | 12 | 12 | 1.4 | 240 | 220 | -20 | 11 | 0 |  | 5 | 0 |  |  | 11 | 4 | 240 | 12
B001 | 8 | 11 | 27 | N |  | 13 | 13 | 0.6 | 248 | 220 | -28 | 11 | 0 |  | 5 | 0 |  |  | 11 | 8 | 248 | 13
B802 | 4 | 12 | 28 | N |  | 13 | 13 | 1.6 | 252 | 240 | -12 | 12 | 0 |  | 5 | 0 |  |  | 12 | 4 | 252 | 13
|  | 15 |  |  |  | #N/A | #N/A |  |  | 300 |  |  | #N/A |  | 1 | 0
|  | 3 | [8 empty] | -36 |  | 0 | #DIV/0!
0
Note on A2: Indicates whether the current plan is feasible (delivery on time with given capacity)
Note on A3: Customer ID
Note on B3: Number of machine-days required
Note on C3: Promised delivery date - Modified
Note on D3: Proposed processing sequence
Note on E3: Priority H - high N - normal L - low
Note on G3: Planned availability - when the orden can be ready (minimum lead time)
Note on J3: Cumulative amount of work (includes all orders up til and including this one)
Note on K3: Cumulative capacity until the promised delivery date.
Note on L3: Slack capacity until this order (this day). Negative indicates unfeasibility - Needs to change promise.
Note on M3: Original promised date. Before making any changes.
Note on N2: =Days delayed*Order Size*Weight Weight: 1 - L 5 - N 10 - H
Note on N3: Whether the order will be late with respect to the original promised delivery date.
Note on O3: Minimum number of days late.

## Details
| Tejidos Especiales e-Dentel. Planner | [5 empty] | Algorithms
Heuristics (quick and dirty) methods for single process scheduling*
1. Miminize sum of completion times of sum of waiting time or number of jobs alive
| Method: | SPT (shortest processing time)
Do jobs in increasing order of processing time
| Example: | Consider the following jobs to be processed by a single machine:
Job | Deliv. | Order | Job | Deliv. | Order | Start | Finish | Delay | Time | No. Jobs | Time | No. Jobs | Time | No. Jobs
A | 5 | 3 | G | 25 | 1 | 0 | 1 | 0 | 0 | 10 | 1 | 10 | 0 | 10
B | 3 | 2 | B | 3 | 2 | 1 | 3 | 0 | 1 | 9 | 3 | 9 | 1 | 10
C | 11 | 5 | F | 8 | 2 | 3 | 5 | 0 | 3 | 8 | 5 | 8 | 1 | 9
D | 15 | 4 | I | 26 | 2 | 5 | 7 | 0 | 5 | 7 | 7 | 7 | 3 | 9
E | 27 | 9 | A | 5 | 3 | 7 | 10 | 5 | 7 | 6 | 10 | 6 | 3 | 8
F | 8 | 2 | D | 15 | 4 | 10 | 14 | 0 | 10 | 5 | 14 | 5 | 5 | 8
G | 25 | 1 | C | 11 | 5 | 14 | 19 | 8 | 14 | 4 | 19 | 4 | 5 | 7
H | 40 | 7 | H | 40 | 7 | 19 | 26 | 0 | 19 | 3 | 26 | 3 | 7 | 7
I | 26 | 2 | J | 31 | 8 | 26 | 34 | 3 | 26 | 2 | 34 | 2 | 7 | 6
J | 31 | 8 | E | 27 | 9 | 34 | 43 | 16 | 34 | 1 | 43 | 1 | 10 | 6
[7 empty] | 162 | 16 |  |  |  |  | 10 | 5
[13 empty] | 14 | 5
[13 empty] | 14 | 4
[13 empty] | 19 | 4
Note that in the first 10 periods we have managed to get half of the jobs through. | [12 empty] | 19 | 3
[13 empty] | 26 | 3
[13 empty] | 26 | 2
[13 empty] | 34 | 2
[13 empty] | 34 | 1
[13 empty] | 43 | 1
[13 empty] | 43 | 0
(*) This is based on a tutorial taught by Prof. Gene Woolsey at an ORSA conference in mid 1980's.
Note on C15: Promised deilvery date
Note on D15: Amount of work in machine-days
Sum of completion times
Maximum tardinesss
4 late jobs

## Details2
| Tedious Especiales e-Dentel. Planner | [5 empty] | Algorithms
Heuristics (quick and dirty) methods for single process scheduling (continued)
2. Miminize maximum tardiness
| Method: | DDR (Due Date Rule)
Do jobs in order of increasing Due Dates
Job | Deliv. | Order | Job | Deliv. | Order | Start | Finish | Delay | Time | No. Jobs | Time | No. Jobs | Time | No. Jobs
A | 5 | 3 | B | 3 | 2 | 0 | 2 | 0 | 0 | 10 | 2 | 10 | 0 | 10
B | 3 | 2 | A | 5 | 3 | 2 | 5 | 0 | 2 | 9 | 5 | 9 | 2 | 10
C | 11 | 5 | F | 8 | 2 | 5 | 7 | 0 | 5 | 8 | 7 | 8 | 2 | 9
D | 15 | 4 | C | 11 | 5 | 7 | 12 | 1 | 7 | 7 | 12 | 7 | 5 | 9
E | 27 | 9 | D | 15 | 4 | 12 | 16 | 1 | 12 | 6 | 16 | 6 | 5 | 8
F | 8 | 2 | G | 25 | 1 | 16 | 17 | 0 | 16 | 5 | 17 | 5 | 7 | 8
G | 25 | 1 | I | 26 | 2 | 17 | 19 | 0 | 17 | 4 | 19 | 4 | 7 | 7
H | 40 | 7 | E | 27 | 9 | 19 | 28 | 1 | 19 | 3 | 28 | 3 | 12 | 7
I | 26 | 2 | J | 31 | 8 | 28 | 36 | 5 | 28 | 2 | 36 | 2 | 12 | 6
J | 31 | 8 | H | 40 | 7 | 36 | 43 | 3 | 36 | 1 | 43 | 1 | 16 | 6
[7 empty] | 185 | 5 |  |  |  |  | 16 | 5
Compare the results with those of the previous | [12 empty] | 17 | 5
heuristic. | [12 empty] | 17 | 4
[13 empty] | 19 | 4
Note now that in the first 10 periods we have managed to get only three of the jobs through. | [12 empty] | 19 | 3
[13 empty] | 28 | 3
[13 empty] | 28 | 2
[13 empty] | 36 | 2
[13 empty] | 36 | 1
[13 empty] | 43 | 1
[13 empty] | 43 | 0
Note on C15: Promised deilvery date
Note on D15: Amount of work in machine-days
Sum of completion times
Maximum tardinesss
5 late jobs

## Details3
| Tedious Especiales e-Dentel. Planner | [6 empty] | Algorithms
Heuristics (quick and dirty) methods for single process scheduling (continued)
3. Maximize Minimum Tardiness
| Method: | Slack Time Rule
Do jobs in increasing order of (Due Date - Processing time)
| Job | Deliv. | Order | Slack | Start | Finish | Delay
| B | 3 | 2 | 1 | 0 | 1 | 0
| A | 5 | 3 | 2 | 1 | 4 | 0
| C | 11 | 5 | 6 | 4 | 9 | 0
| F | 8 | 2 | 6 | 9 | 11 | 3
| D | 15 | 4 | 11 | 11 | 15 | 0
| E | 27 | 9 | 18 | 15 | 24 | 0
| J | 31 | 8 | 23 | 24 | 32 | 1
| G | 25 | 1 | 24 | 32 | 33 | 8
| I | 26 | 2 | 24 | 33 | 35 | 9
| H | 40 | 7 | 33 | 35 | 42 | 2
4. Minimize Maximum Tardiness relative to priority
| Method: | Ratio Rule
Do jobs in increasing order of (Due Date-Processing time)/Priority
| Note: | The higher the priority, the bigger the priority number
| Job | Deliv. | Order | Priority | Ratio | Start | Finish | Delay
| B | 3 | 2 | 5 | 0.2 | 0 | 2 | 0
| A | 5 | 3 | 3 | 0.66667 | 2 | 5 | 0
| C | 11 | 5 | 4 | 1.5 | 5 | 10 | 0
| D | 15 | 4 | 5 | 2.2 | 10 | 14 | 0
| F | 8 | 2 | 2 | 3 | 14 | 16 | 8
| G | 25 | 1 | 5 | 4.8 | 16 | 17 | 0
| I | 26 | 2 | 3 | 8 | 17 | 19 | 0
| E | 27 | 9 | 1 | 18 | 19 | 28 | 1
| J | 31 | 8 | 1 | 23 | 28 | 36 | 5
| H | 40 | 7 | 1 | 33 | 36 | 43 | 3
5 late jobs
4 late jobs, all with
low priority

## Details4
| Tedious Especiales e-Dentel. Planner | [5 empty] | Algorithms
Heuristics (quick and dirty) methods for single process scheduling (continued)
5. Minimize the number of late jobs
| Method: | Moores's method
a) Put jobs in increasing order of Due Dates
b) Start doing the jobs from top to bottom until a late job is found
c) Look at all the jobs up to an including the late one. From these jobs, pick out the
one with the biggest processing time. Remove it from the list and put it last.
d) If all jobs are not yet scheduled, go to step (b)
e) Sort the jobs you removed from the list in increasing order of Due Date.
| Job | Deliv. | Order | Start | Finish | Delay
| B | 3 | 2 | 0 | 2 | 0
| A | 5 | 3 | 2 | 5 | 0
| F | 8 | 2 | 5 | 7 | 0
| C | 11 | 5 | 7 | 12 | 1
| D | 15 | 4 | 12 | 16 | 1
| G | 25 | 1 | 16 | 17 | 0
| I | 26 | 2 | 17 | 19 | 0
| E | 27 | 9 | 19 | 28 | 1
| J | 31 | 8 | 28 | 36 | 5
| H | 40 | 7 | 36 | 43 | 3
From these jobs, select the one with the biggest processing time and remove it from the list,
putting it last. Recompute delays.
| Job | Deliv. | Order | Start | Finish | Delay
| B | 3 | 2 | 0 | 2 | 0
| A | 5 | 3 | 2 | 5 | 0
| F | 8 | 2 | 5 | 7 | 0
| D | 15 | 4 | 7 | 11 | 0
| G | 25 | 1 | 11 | 12 | 0
| I | 26 | 2 | 12 | 14 | 0
| E | 27 | 9 | 14 | 23 | 0
| J | 31 | 8 | 23 | 31 | 0
| H | 40 | 7 | 31 | 38 | 0
| C | 11 | 5 | 38 | 43 | 32
Note: in this case, we have had to do only one iteration, but in other cases you may need
to repeat the process several times.
First late job
No more late jobs
in the list
Only 1 late job

## Cumulative
Return
Print

## PrPlan
Return
Print

## Capacity (hidden)
Daily capacity (in machine*days).
| Day | Capacity | Cum. Cap. | Day
| 0 | 0 | 0 | 0
| 1 | 20 | 20 | 1
| 2 | 20 | 40 | 2
| 3 | 20 | 60 | 3
| 4 | 20 | 80 | 4
| 5 | 20 | 100 | 5
| 6 | 20 | 120 | 6
| 7 | 20 | 140 | 7
| 8 | 20 | 160 | 8
| 9 | 20 | 180 | 9
| 10 | 20 | 200 | 10
| 11 | 20 | 220 | 11
| 12 | 20 | 240 | 12
| 13 | 20 | 260 | 13
| 14 | 20 | 280 | 14
| 15 | 20 | 300 | 15
Note on C4: Maximum capacity in each day. Default is 20.

## Orig (hidden)
Customer | Order | Delivery | Prior. | Comments | Cum. Order | Cum Cap. | Dif.
|  | 0 |  |  | 0 | 0
A100 | 6 | 3 | H | Riesgo anulación | 6 | 60 | 54
A137 | 2 | 3 | N |  | 8 | 60 | 52
A400 | 4 | 4 | H |  | 12 | 80 | 68
B108 | 8 | 4 | N |  | 20 | 80 | 60
B400 | 10 | 5 | N | Admite entregas parciales | 30 | 100 | 70
A400 | 8 | 5 | L |  | 38 | 100 | 62
A238 | 6 | 5 | N |  | 44 | 100 | 56
B007 | 10 | 6 | H | Podría servirse una parte y retrasar otra | 54 | 120 | 66
B009 | 12 | 6 | H |  | 66 | 120 | 54
C017 | 12 | 6 | N | Admite entregas adelantadas | 78 | 120 | 42
C018 | 10 | 6 | N | Admite entregas adelantadas | 88 | 120 | 32
A200 | 5 | 7 | L | Admite entregas adelantadas | 93 | 140 | 47
A203 | 5 | 7 | N | Admite entregas adelantadas | 98 | 140 | 42
A537 | 10 | 7 | N |  | 108 | 140 | 32
A211 | 14 | 7 | H | Riesgo anulación | 122 | 140 | 18
A219 | 10 | 7 | N |  | 132 | 140 | 8
B105 | 4 | 7 | N |  | 136 | 140 | 4
B107 | 10 | 8 | N |  | 146 | 160 | 14
B217 | 5 | 8 | N |  | 151 | 160 | 9
A100 | 3 | 8 | H |  | 154 | 160 | 6
B455 | 3 | 8 | N |  | 157 | 160 | 3
B128 | 15 | 8 | H | Riesgo anulación; Buen cliente | 172 | 160 | -12
B213 | 10 | 9 | N |  | 182 | 180 | -2
B800 | 20 | 9 | N | Admite entregas parciales | 202 | 180 | -22
A431 | 10 | 9 | N |  | 212 | 180 | -32
A470 | 4 | 9 | N |  | 216 | 180 | -36
A503 | 10 | 10 | N |  | 226 | 200 | -26
A137 | 10 | 10 | N |  | 236 | 200 | -36
B001 | 8 | 11 | N |  | 244 | 220 | -24
B813 | 4 | 11 | N |  | 248 | 220 | -28
B802 | 4 | 12 | N |  | 252 | 240 | -12

## MaxDelay (hidden)
Customer | Order | Delivery | Prior. | Comments | Cum. Order | Cum Cap. | Dif. | Day | Available
|  | 0 |  |  | 0 | 0 |  | 0 | 17
A100 | 6 | 3 | A | Riesgo anulación | 6 | 60 | 54 | 3 | 17
A400 | 4 | 4 | A |  | 10 | 80 | 70 | 4 | 17
A137 | 2 | 5 | N |  | 12 | 100 | 88 | 5 | 17
B108 | 8 | 6 | N |  | 20 | 120 | 100 | 6 | 17
B007 | 10 | 6 | A | Podría servirse una parte y retrasar otra | 30 | 120 | 90 | 6 | 17
B009 | 12 | 6 | A |  | 42 | 120 | 78 | 6 | 17
B400 | 10 | 7 | N | Admite entregas parciales | 52 | 140 | 88 | 7 | 17
A238 | 6 | 7 | N |  | 58 | 140 | 82 | 7 | 17
A211 | 14 | 7 | A | Riesgo anulación | 72 | 140 | 68 | 7 | 17
C017 | 12 | 8 | N | Admite entregas parciales | 84 | 160 | 76 | 8 | 17
C018 | 10 | 8 | N | Admite entregas parciales | 94 | 160 | 66 | 8 | 17
A100 | 3 | 8 | A |  | 97 | 160 | 63 | 8 | 17
B128 | 15 | 8 | A | Riesgo anulación; Buen cliente | 112 | 160 | 48 | 8 | 17
A203 | 5 | 9 | N | Admite entregas parciales | 117 | 180 | 63 | 9 | 17
A537 | 10 | 9 | N |  | 127 | 180 | 53 | 9 | 17
A219 | 10 | 9 | N |  | 137 | 180 | 43 | 9 | 17
B105 | 4 | 9 | N |  | 141 | 180 | 39 | 9 | 17
B107 | 10 | 10 | N |  | 151 | 200 | 49 | 10 | 17
B217 | 5 | 10 | N |  | 156 | 200 | 44 | 10 | 17
B455 | 3 | 10 | N |  | 159 | 200 | 41 | 10 | 17
B213 | 10 | 11 | N |  | 169 | 220 | 51 | 11 | 17
B800 | 20 | 11 | N | Admite entregas parciales | 189 | 220 | 31 | 11 | 17
A431 | 10 | 11 | N |  | 199 | 220 | 21 | 11 | 17
A470 | 4 | 11 | N |  | 203 | 220 | 17 | 11 | 17
A503 | 10 | 12 | N |  | 213 | 240 | 27 | 12 | 17
A137 | 10 | 12 | N |  | 223 | 240 | 17 | 12 | 17
B001 | 8 | 13 | N |  | 231 | 260 | 29 | 13 | 25
B813 | 4 | 13 | N |  | 235 | 260 | 25 | 13 | 25
B802 | 4 | 14 | N |  | 239 | 280 | 41 | 14 | 41
A400 | 8 | 15 | B |  | 247 | 300 | 53 | 15 | 48
A200 | 5 | 15 | B | Admite entregas parciales | 252 | 300 | 48 | 15 | 48

## MaxDelay2 (hidden)
Customer | Order | Delivery | Prior. | Comments | Cum. Order | Cum Cap. | Dif.
|  | 0 |  |  | 0 | 0
A100 | 6 | 3 | A | Riesgo anulación | 6 | 60 | 54
A400 | 4 | 4 | A |  | 10 | 80 | 70
A137 | 2 | 5 | N |  | 12 | 100 | 88
| 50 | 5 |  |  | 62 | 100 | 38
B108 | 8 | 6 | N |  | 70 | 120 | 50
B007 | 10 | 6 | A | Podría servirse una parte y retrasar otra | 80 | 120 | 40
B009 | 12 | 6 | A |  | 92 | 120 | 28
B400 | 10 | 7 | N | Admite entregas parciales | 102 | 140 | 38
A238 | 6 | 7 | N |  | 108 | 140 | 32
A211 | 14 | 7 | A | Riesgo anulación | 122 | 140 | 18
C017 | 12 | 8 | N | Admite entregas parciales | 134 | 160 | 26
C018 | 10 | 8 | N | Admite entregas parciales | 144 | 160 | 16
A100 | 3 | 8 | A |  | 147 | 160 | 13
B128 | 15 | 8 | A | Riesgo anulación; Buen cliente | 162 | 160 | -2
A203 | 5 | 9 | N | Admite entregas parciales | 167 | 180 | 13
A537 | 10 | 9 | N |  | 177 | 180 | 3
A219 | 10 | 9 | N |  | 187 | 180 | -7
B105 | 4 | 9 | N |  | 191 | 180 | -11
B107 | 10 | 10 | N |  | 201 | 200 | -1
B217 | 5 | 10 | N |  | 206 | 200 | -6
B455 | 3 | 10 | N |  | 209 | 200 | -9
B213 | 10 | 11 | N |  | 219 | 220 | 1
B800 | 20 | 11 | N | Admite entregas parciales | 239 | 220 | -19
A431 | 10 | 11 | N |  | 249 | 220 | -29
A470 | 4 | 11 | N |  | 253 | 220 | -33
A503 | 10 | 12 | N |  | 263 | 240 | -23
A137 | 10 | 12 | N |  | 273 | 240 | -33
B001 | 8 | 13 | N |  | 281 | 260 | -21
B813 | 4 | 13 | N |  | 285 | 260 | -25
B802 | 4 | 14 | N |  | 289 | 280 | -9
A400 | 8 | 15 | B |  | 297 | 300 | 3
A200 | 5 | 15 | B | Admite entregas parciales | 302 | 300 | -2

## Datos (hidden)
Order | Orig. Del.
A100 | 3
A101 | 8
A137 | 3
A138 | 10
A200 | 7
A203 | 7
A211 | 7
A219 | 7
A238 | 5
A400 | 4
A401 | 5
A431 | 9
A470 | 9
A503 | 10
A537 | 7
B001 | 11
B007 | 6
B009 | 6
B105 | 7
B107 | 8
B108 | 4
B128 | 8
B213 | 9
B217 | 8
B400 | 5
B455 | 8
B800 | 9
B802 | 12
B813 | 11
C017 | 6
C018 | 6